## Sheet1
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints. | Guidelines
Example : All tasks were completed on time. Team communication was seamless. | Requirements changed mid-sprint. | Plan for a buffer to handle scope changes. | Set stricter deadlines for finalizing requirements. | Example
| - All prediction modules were integrated successfully into the unified Streamlit dashboard. | - Requirements changed mid-sprint, leading to rushed modifications. | - Allocate a buffer period to accommodate any last-minute requirement changes. | - Set stricter deadlines for finalizing requirements before sprint start.
| - Effective team communication and knowledge sharing supported quick problem resolution. | - Data integration challenges were encountered, affecting timely model training. | - Enhance documentation for data pipelines and model workflows for improved onboarding and troubleshooting. | - Organize regular check-ins with stakeholders to ensure alignment on requirements and technical dependencies.
| - The implementation of explainability features (e.g., feature importance charts) was well received. | - Some modules (e.g., the GNN for heart disease) took longer to optimize due to data sparsity. | - Brainstorm automated testing strategies to catch integration issues earlier in the process. | - Plan for a post-sprint review meeting focusing on integrating clinician feedback, with actionable items for improved testing and error logging.
| - The modular design approach allowed efficient parallel development and testing across teams. | - Minor delays in retraining models because of unexpected runtime errors in the pipeline. | - Consider incorporating a more robust error logging and alert system to ensure quick fixes in case of similar issues. | - Streamline the development process by adopting automated data-validation and testing routines before deployment.
| All tasks were completed on time. | Requirements changed mid-sprint. | Plan for a buffer period to address scope changes. | Set stricter deadlines for finalizing requirements before sprint kickoff.
| Team communication was seamless overall. | Occasional communication breakdowns with remote members. | Schedule regular stand-up meetings. | Hold daily quick huddles to ensure alignment among team members.
| The modular UI design accelerated integration testing. | Some UI components faced compatibility issues on older browsers. | Initiate cross-browser testing early in the sprint. | Integrate automated browser testing into the CI/CD pipeline.
| Model explainability features received positive clinical feedback. | Certain outputs were challenging for non-technical users. | Develop simplified visualization tutorials. | Organize training sessions to help users interpret model outputs.
| Automated model training scripts reduced manual effort significantly. | Intermittent server downtime disrupted training schedules. | Implement redundant server backup systems. | Set up robust monitoring and failover systems to minimize downtime.
| Comprehensive documentation improved overall clarity. | Some parts of the documentation were incomplete or outdated. | Establish a collaborative review process for documentation. | Schedule periodic documentation review sessions with the full team.
| Integration with real-time data was successfully achieved. | Data flow occasionally slowed due to network issues. | Optimize the data pipeline to enhance real-time performance. | Investigate current network infrastructure and plan targeted upgrades.
| Built-in validation minimized data entry errors effectively. | Handling of edge cases in validation was inconsistent. | Add more comprehensive and robust validation checks. | Update the validation module and conduct targeted testing for edge cases.